## Sheet 1
Defect # | Status | Raised By | Tested on Version | Date found on | TestCase Id | Steps to Reproduce | Description | Priority | Severity
1 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewAcc1-1 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Leave "Customer ID" field empty 5. Press Tab to move to the next field 6. System error: "Customer ID field cannot be empty" must be shown | No system error message is shown | Medium | Medium
2 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewAcc1-2 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Enter "1234$" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Special characters are not allowed" must be shown | No system error message is shown | Medium | Medium
3 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewAcc1-3 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Enter "1234S" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Characters are not allowed" must be shown | No system error message is shown | Medium | Medium
4 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewAcc1-3_1 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Enter " 12345" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Customer ID cannot have space as the first character" must be shown | No system error message is shown | Medium | Medium
5 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-7 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " 12345" to Customer name field 5. Press Tab to move to the next field 6. System error: "First chacracter cannot have space" must be shown | No system error message is shown | Medium | Medium
6 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-8 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Leave Address field blank 5. Press Tab to move to the next field 6. System error: "Address field cannot be empty" must be shown | No system error message is shown | Medium | Medium
7 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-9 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " Brighton Beach" to Address field 5. Press Tab to move to the next field 6. System error: "Address field cannot have space as the first character" must be shown | No system error message is shown | Medium | Medium
8 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-10 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter "Brighton Be@ch" to Address field 5. Press Tab to move to the next field 6.System error: "Special characters are not allowed" msut be shown | No system error message is shown | Medium | Medium
9 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-14 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " New York" to City field 5. Press Tab to move to the next field 6. System error: "City cannot have space as the first character" must be shown | System error "Numbers are not allowed" appears instead of "City cannot have space as the first character" | Medium | Medium
10 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-17_1 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " USA" to State field 5. Press Tab to move to the next field 6. System error: "State cannot have space as the first character" must be shown | System error "Numbers are not allowed" is shown instead of "State cannot have space as the first character" | Medium | Low
11 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-22 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " 12345" to PIN field 5. Press Tab to move to the next field 6. System error: "PIN Code cannot have space as the first character"or "PIN Code must have 6 Digits" must be shown | No system error message is shown | Medium | Medium
12 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-26 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " 0534089275" to Telephone Number field 5. Press Tab to move to the next field 6.System error: "Telephone number cannot have space as the first character " must be shown | No system error message is shown | Medium | Medium
13 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | NewCus-2-29 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Enter " test@gmail.com" to Email field 5. Press Tab to move to the next field 6. System error: "Email cannot have space as the first character" must be showm | No system error message is shown | Medium | Medium
14 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | CusSta-4-36 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Enter "!2345" to Amount Lower Limit field 5. Press Tab to move to the next field 6. System error: "Special characters are not allowed" must be shown | No system error message is shown | Medium | Medium
15 | Open | Shreyas Bhagat | v1 | 2024-07-19 | CusSta-4-37 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Amount Lower Limit field blank 5. Press Tab to move to the next field 6. System error: "Amount Lower Limit must not be blank" must be shown | No system error message is shown | Medium | Medium
16 | Open | Shreyas Bhagat | v1 | 2024-07-19 | CusSta-4-38 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Enter "I2345" to Amount Lower Limit field 5. Press Tab to move to the next field 6. System error: "Characters are not allowed" must be shown | No system error message is shown | Medium | Medium
17 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | CusSta-4-39 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Enter "!2345" to Number of Transaction field 5. Press Tab to move to the next field 6. System error: "Special characters are not allowed" must be shown | No system error message is shown | Medium | Medium
18 | Open | Shreyas Bhagat | v1 | 2024-07-19 | CusSta-4-40 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Number of Transaction field blank 5. Press Tab to move to the next field 6. System error: "Number of transaction must not be blank" must be shown | No system error message is shown | Medium | Medium
19 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | CusSta-4-41 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Enter "I2345" to Number of Transaction field 5. Press Tab to move to the next field 6. System error: "Characters are not allowed" must be shown | No system error message is shown | Medium | Medium
20 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | DelCus-6-47 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to Delete Customer page 4. Enter "I2345" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Characters are not allowed" must be shown | No system error message is shown | Medium | Medium
21 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | DelCus-6-47_1 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to Delete Customer page 4. Enter " 12345" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Customer ID cannot have space as the first character " must be shown | No system error message is shown | Medium | Medium
22 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | EdiCus-9-60 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to Edit Customer page 4. Enter "1234S" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Customer ID cannot have characters" must be shown | No system error message is shown | Medium | Medium
23 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | EdiCus-9-60_1 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to Edit Customer page 4. Enter " 12345" to Customer ID field 5. Press Tab to move to the next field 6. System error: "Customer ID cannot have space as the first character " must be shown | No system error message is shown | Medium | Medium
24 | Open | Shreyas Bhagat | v1 | 2024-07-19 | CusUI_B | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Verify that Account No, Amount Lower Limit and Number Of Transaction fields are marked as "* mandatory field" | Amount Lower Limit and Number Of Transaction fields are not marked as mandatory | Low | Low
25 | Open | Shreyas Bhagat | v1 | 2024-07-19 | NewCusUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Verify that fields' labels are as required | "E-mail" label instead of "Email Id" | Low | Low
26 | Open | Shreyas Bhagat | v1 | 2024-07-19 | NewCusUI_B | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Verify that all fields are marked as "* mandatory field" | Telephone Number field is not marked as mandatory | Low | Low
27 | Open | Shreyas Bhagat | v1 | 2024-07-19 | NewAccUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that fields' labels are as required | "Customer id" instead of "Customer Id", "Account type" instead of "Account Type", "submit" instead of "Submit" and "reset" instead of "Reset" labels | Low | Low
28 | Open | Shreyas Bhagat | v1 | 2024-07-19 | NewAccUI_B | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | Customer id, Account type and Initial deposit fields are marked (*) instead of * sign | Low | Low
29 | Open | Shreyas Bhagat | v1 | 2024-07-19 | DelCusUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
30 | Open | Shreyas Bhagat | v1 | 2024-07-19 | EdiAccUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager= 3. Navigate to "Edit Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
31 | Open | Shreyas Bhagat | v1 | 2024-07-19 | DelAccUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager= 3. Navigate to "Delete Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
32 | Open | Shreyas Bhagat | v1 | 2024-07-19 | EdiCusUi_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
33 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | LogUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Navigate to "Login" page 3. Verify that fields' labels are as required | "Gtpl Bank" instead of "Guru99 Bank" | High | Low
34 | Open | Shreyas Bhagat | v1 | 2024-07-19 | LogUI_B | 1. Open http://demo.guru99.com/V1/index.php 2. Verify that all fields are marked as "* mandatory field" | UserID and Password fields are marked (*) instead of * sign | Low | Low
35 | Open | Shreyas Bhagat | v1 | 2024-07-19 | HomeUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Home page" page 4. Verify that fields' labels are as required | "Gtpl Bank" instead of "Guru99 Bank" label and "Welcome to Manager's page of Gtpl Bank" welcome message instead of "Welcome to Manager's page of Guru99 Bank" | High | Low
36 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | IP1 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Add New Customer with this data: Kate Female 17.01.1995 Address - Molon City - Holon State - Bolon PIN - 380009 Telephone - 8000187025 Email - rafasgj@mac.com 5. Press "Submit" button 6. New Customer should be added successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
37 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | IP6 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Add New Account with this data: customer id -17283 account type-saving/current Initial Deposit-500 5. Press "Submit" button 6. New Account should be added successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
38 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | IP8 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Mini Statement" page 4. Generate Mini Statement with this data: Account Number = "95419" 5. Press "Submit" button 6. Mini Statement should be generated successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
39 | Open | Shreyas Bhagat | v1 | 2024-07-19 | IP10 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Customized Statement" page 4. Generate Customized Statement with this data: Account number = "95419" From Date = "19.07.2021" To Date = "29.07.2021" Minimum Transaction Value = "500" Number of Transaction = "1" 5. Press "Submit" button 6. Customized Statement should be generated successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
40 | Open | Shreyas Bhagat | v1 | 2024-07-19 | IP11 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Delete Account" page 4. Delete Account with this data: Account No = "95419" 5. Press "Submit" button 6. Account should be deleted successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
41 | Closed | Shreyas Bhagat | v1 | 2024-07-19 | IP15 | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Delete Customer with this data: Customer Id = "69728" 5. Press "Submit" button 6. Customer should be deleted successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
(v2)
42 | Duplicate | Shreyas Bhagat | v2 | 2024-07-29 | CusSta-4-37 | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Amount Lower Limit field blank 5. Press Tab to move to the next field 6. System error: "Amount Lower Limit must not be blank" must be shown | No system error message is shown | Medium | Medium
43 | Duplicate | Shreyas Bhagat | v2 | 2024-07-29 | CusSta-4-40 | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Number of Transaction field blank 5. Press Tab to move to the next field 6. System error: "Number of transaction must not be blank" must be shown | No system error message is shown | Medium | Medium
44 | Closed | Shreyas Bhagat | v2 | 2024-07-29 | EdiCus-25-34 | 1. Open http://demo.guru99.com/V2/ 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Enter Customer ID = "17283" 4. Enter "sanjayrathod273@gmail.com" to Email ID field 5. Press "Submit" button 6. System error: "This Email is already used" must be shown | System message: "Customer records updated successfully!" | High | Medium
45 | Open | Shreyas Bhagat | v2 | 2024-07-29 | CusSta-27-40 | 1. Open http://demo.guru99.com/V2/ 2. Login as a manager 3. Navigate to "Customized Statement" page 4. Enter data: Account No = "95420" From Date = "29/08/2021" To Date = "29/07/2021" 5. Press "Submit" button 6. System error: "Choose correct date" must be shown | System error:" No Transaction details found !!!" | Low | Low
46 | Open | Shreyas Bhagat | v2 | 2024-07-29 | MinSta-28-44 | 1. Open http://demo.guru99.com/V2/ 2. Login as a manager 3. Navigate to "Mini Statement" page 4. Enter data: Account No = "95420" Transaction = "456732" 5. Press "Submit" button 6. System error: "This transaction doesn't exist" must be shown | Field "Transaction" doesn't exist | Medium | Medium
47 | Open | Shreyas Bhagat | v2 | 2024-07-29 | BalUI_B | 1. Open http://demo.guru99.com/V2/ 2. Login as a manager/customer 3. Navigate to "Balance Enquiry" page 4. Verify that all required fields are marked as "*mandatory fields" | "Account No" field is not marked as mandatory | Low | Low
48 | Open | Shreyas Bhagat | v2 | 2024-07-29 | CusUI_B | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Verify that Account No, Minimum Transaction Value, Number Of Transaction fields are marked as "* mandatory field" | Minimum Transaction Value and Number Of Transaction fields are not marked as mandatory | Low | Low
49 | Open | Shreyas Bhagat | v2 | 2024-07-29 | NewCusUI_A | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Verify that fields' labels are as required | "E-mail" label instead of "Email Id" | Low | Low
50 | Open | Shreyas Bhagat | v2 | 2024-07-29 | NewCusUI_B | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
51 | Open | Shreyas Bhagat | v2 | 2024-07-29 | NewAccUI_A | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that fields' labels are as required | "Customer id" instead of "Customer Id", "Account type" instead of "Account Type", "submit" instead of "Submit" and "reset" instead of "Reset" labels | Low | Low
52 | Open | Shreyas Bhagat | v2 | 2024-07-29 | NewAccUI_B | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
53 | Open | Shreyas Bhagat | v2 | 2024-07-29 | DelCusUI_A | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
54 | Open | Shreyas Bhagat | v2 | 2024-07-29 | EdiAccUI_A | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "Edit Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
55 | Open | Shreyas Bhagat | v2 | 2024-07-29 | EdiAccForUI | 1. Open http://demo.guru99.com/V2/ 2. Login as a manager/customer 3. Navigate to "Edit Account form" page 4. Verify that fields' labels are as required | System error: "You are not authorize to edit this Account!!" | High | Medium
56 | Open | Shreyas Bhagat | v2 | 2024-07-29 | DelAccUI_A | 1. Open http://demo.guru99.com/V1/index.php 2. Login as a manager= 3. Navigate to "Delete Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
57 | Open | Shreyas Bhagat | v2 | 2024-07-29 | EdiCusUi_A | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Verify that fields' labels are as required | "Infy Bank" headline instead of "Guru99 Bank", "Customer ID" instead of "Customer Id" label | High | Low
58 | Open | Shreyas Bhagat | v2 | 2024-07-29 | LogUI_B | 1. Open http://demo.guru99.com/V2/index.php 2. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
59 | Closed | Shreyas Bhagat | v2 | 2024-07-29 | HomeUI_A | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "Home page" page 4. Verify that fields' labels are as required | Deposit Withdrawal Fund Transfer Change Password sections do not exist | High | Low
60 | Open | Shreyas Bhagat | v2 | 2024-07-29 | IP11 | 1. Open http://demo.guru99.com/V2/index.php 2. Login as a manager 3. Navigate to "Delete Account" page 4. Delete Account with this data: Account No = "95419" 5. Press "Submit" button 6. Account should be deleted successfully | System error message "Could not connect: Access denied for user 'root'@'localhost' (using password: NO)" is shown | High | High
(v3)
61 | Duplicate | Shreyas Bhagat | v3 | 2024-07-30 | CusSta-4-37 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Amount Lower Limit field blank 5. Press Tab to move to the next field 6. System error: "Amount Lower Limit must not be blank" must be shown | No system error message is shown | Medium | Medium
62 | Duplicate | Shreyas Bhagat | v3 | 2024-07-30 | CusSta-4-40 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Number of Transaction field blank 5. Press Tab to move to the next field 6. System error: "Number of transaction must not be blank" must be shown | No system error message is shown | Medium | Medium
63 | Open | Shreyas Bhagat | v3 | 2024-07-30 | ChaPas-14-103 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager/customer 3. Navigate to "Change Password" page 4. Enter same passwords to Old Password and New Password fields 5. Confirm New Password and Submit 6. System error: "New Password should not match Old Password" must be shown | No system error message is shown | Medium | Medium
64 | Open | Shreyas Bhagat | v3 | 2024-07-30 | BalEnq-16-3-B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager/customer 3. Navigate to "Balance Enquiry" page 4. Enter Account Number not associated with manager or customer 5. Press "Submit" button 6. System error: "You are not authorized to view this page" must be shown | Balance Enquiry page of Account not associated is opened | High | Medium
65 | Open | Shreyas Bhagat | v3 | 2024-08-02 | EdiCus-25-34 | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Enter Customer ID = "17283" 4. Enter "sanjayrathod273@gmail.com" to Email ID field 5. Press "Submit" button 6. System error: "This Email is already used" must be shown | System message: "Customer records updated successfully!" | High | Medium
66 | Open | Shreyas Bhagat | v3 | 2024-08-02 | FunTra-17-6 | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager 3. Navigate to "Fund Transfer" page 4. Enter same Payers and Payees Account Numbers to related fields 5. Press "Submit" button 6. System error: "Payers and Payees Account numbers should not match!!" must be shown | Fund Transafer Details page is shown | Medium | Medium
67 | Open | Shreyas Bhagat | v3 | 2024-08-02 | FunTra-17-8 | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager 3. Navigate to "Fund Transfer" page 4. Enter Account number not associated with manager to Payers Account number field 5. Press "Submit" button 6. System error: "You are not authorized to do this!!" must be shown | Fund Transafer Details page is shown | High | High
68 | Open | Shreyas Bhagat | v3 | 2024-08-02 | FunTra-17-10 | 1. Open http://demo.guru99.com/V3/ 2. Login as a customer 3. Navigate to "Fund Transfer" page 4. Enter same Payers and Payees Account Numbers to related fields 5. Press "Submit" button 6. System error: "Payers and Payees Account numbers should not match!!" must be shown | Fund Transafer Details page is shown | Medium | Medium
69 | Open | Shreyas Bhagat | v3 | 2024-08-02 | FunTra-17-12 | 1. Open http://demo.guru99.com/V3/ 2. Login as a customer 3. Navigate to "Fund Transfer" page 4. Enter Account number not associated with manager to Payers Account number field 5. Press "Submit" button 6. System error: "You are not authorized to do this!!" must be shown | Fund Transafer Details page is shown | High | High
70 | Open | Shreyas Bhagat | v3 | 2024-08-02 | WD-18-14 | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager 3. Navigate to "Withdrawal" page 4. Enter Account number that doesn't have necessary balance 5. Enter Amount that is greater than current balance amount 6. Press "Submit" button 7. System error: "Transaction Failed. Account Balance Low!!!" must be shown | Withdrawal Details page is shown | High | High
71 | Open | Shreyas Bhagat | v3 | 2024-08-02 | ChaPas-26-38 | 1. Open http://demo.guru99.com/V3/ 2. Login as a customer 3. Navigate to "Change Password" page 4. Enter Old Password that is not associated with customer ID 5. Enter New Password and Confirm 6. Press "Submit" button 7. System error: "Password is invalid" must be shown | Blank page is opened when trying to change password with non-existent old password | Medium | Medium
72 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | CusSta-27-40 | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager 3. Navigate to "Customized Statement" page 4. Enter data: Account No = "95420" From Date = "29/08/2021" To Date = "29/07/2021" 5. Press "Submit" button 6. System error: "Choose correct date" must be shown | System error:" No Transaction details found !!!" is shown | Low | Low
73 | Open | Shreyas Bhagat | v3 | 2024-08-02 | CusSta-27-42 | 1. Open http://demo.guru99.com/V3/ 2. Login as a customer 3. Navigate to "Customized Statement" page 4. Enter data: Account No = "95420" From Date = "29/08/2021" To Date = "29/07/2021" 5. Press "Submit" button 6. System error: "Choose correct date" must be shown | System error:" No Transaction details found !!!" is shown | Low | Low
74 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | MinSta-28-44 | 1. Open http://demo.guru99.com/V2/ 2. Login as a manager 3. Navigate to "Mini Statement" page 4. Enter data: Account No = "95420" Transaction = "456732" 5. Press "Submit" button 6. System error: "This transaction doesn't exist" must be shown | Field "Transaction" doesn't exist | Medium | Medium
75 | Open | Shreyas Bhagat | v3 | 2024-08-02 | MinSta-28-47 | 1. Open http://demo.guru99.com/V3/ 2. Login as a customer 3. Navigate to "Mini Statement" page 4. Enter Account Number that does not associate wuth customer 5. Press "Submit" button 6. System error: "You are not authorized to to this!" must be shown | Mini Statement page of non-associated account is opened | High | Medium
76 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | BalUI_B | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager/customer 3. Navigate to "Balance Enquiry" page 4. Verify that all required fields are marked as "*mandatory fields" | "Account No" field is not marked as mandatory | Low | Low
77 | Open | Shreyas Bhagat | v3 | 2024-08-02 | FunUI | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager/customer 3. Navigate to "Fund Transfer" page 4. Verify that fields' labels are as required | Description field is present though not mentioned on STR document | Low | Low
78 | Open | Shreyas Bhagat | v3 | 2024-08-02 | MinUI_B | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager/customer 3. Navigate to "Mini Statement" page 4. Verify that Account No field is marked as "*mandatory fields" | Account No is not marked as mandatory | Low | Low
79 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | CusUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Verify that Account No, Minimum Transaction Value, Number Of Transaction fields are marked as "* mandatory field" | Account Number, Minimum Transaction Value and Number Of Transaction fields are not marked as mandatory | Low | Low
80 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | NewCusUI_A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Verify that fields' labels are as required | "E-mail" label instead of "Email Id" and Password field is present though not described in STR document | Low | Low
81 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | NewCusUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
82 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | NewAccUI_A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that fields' labels are as required | "Customer id" instead of "Customer Id", "Account type" instead of "Account Type", "submit" instead of "Submit" and "reset" instead of "Reset" labels | Low | Low
83 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | NewAccUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
84 | Open | Shreyas Bhagat | v3 | 2024-08-02 | DepUI-A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Deposit" page 4. Verify that fields' labels are as required | "Amount" instead of "Amount Deposut" field | Low | Low
85 | Open | Shreyas Bhagat | v3 | 2024-08-02 | DepUI-B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Deposit" page 4. Verify that all fields are marked as "* mandatory field" | Account Number, Amount and Description fields are not marked as mandatory | Low | Low
86 | Open | Shreyas Bhagat | v3 | 2024-08-02 | WitUI-B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Withdrawal" page 4. Verify that all fields are marked as "* mandatory field" | Account Number, Amount and Description fields are not marked as mandatory | Low | Low
87 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | DelCusUI_A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
88 | Open | Shreyas Bhagat | v3 | 2024-08-02 | DelCusUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Verify that all fields are marked as "* mandatory field" | Customer ID is not marked as mandatory field | Low | Low
89 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | EdiAccUI_A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Edit Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
90 | Open | Shreyas Bhagat | v3 | 2024-08-02 | EdiAccUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Edit Account" page 4. Verify that all fields are marked as "* mandatory field" | Account No field is not marked as mandatory | Low | Low
91 | Open | Shreyas Bhagat | v3 | 2024-08-02 | EdiAccForUI | 1. Open http://demo.guru99.com/V3/ 2. Login as a manager/customer 3. Navigate to "Edit Account form" page 4. Verify that fields' labels are as required | "Type of Account" instead of "Account Type" and "Savings" instead of "Saving" in dropdown list | Low | Low
92 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | DelAccUI_A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager= 3. Navigate to "Delete Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
93 | Open | Shreyas Bhagat | v3 | 2024-08-02 | DelAccUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager= 3. Navigate to "Delete Account" page 4. Verify that all fields are marked as "* mandatory field" | Account No field is not marked as mandatory | Low | Low
94 | Open | Shreyas Bhagat | v3 | 2024-08-02 | EdiCusUI_A | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
95 | Open | Shreyas Bhagat | v3 | 2024-08-02 | EdiCusUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Verify that all fields are marked as "* mandatory field" | Customer ID is not marked as mandatory field | Low | Low
96 | Duplicate | Shreyas Bhagat | v3 | 2024-08-02 | LogUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
97 | Open | Shreyas Bhagat | v3 | 2024-08-02 | HomeUI_B | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a customer 3. Navigate to Home page 4. Verify that fields' labels are as required | "Changepassword" section is mistyped | Low | Low
98 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM1 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a customer 3. Navigate to Change Password page 4. Enter Incorrect Old Password to Old Password field 5. Enter New Password and Confirm 6. System error "Invalid Old Password" should be shown | Redirected to blank page without changes in password | Medium | Low
99 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM6 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Delete Account page 4. Enter Account number 5. Press "Submit" button 6. System pop-up message "Do you really want to delete this account?" should be shown | No pop-up confirmation message | Medium | Low
100 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM11 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Delete Customer page 4. Enter Customer ID 5. Press "Submit" button 6. System pop-up message "Do you really want to delete this customer?" should be shown | No pop-up confirmation message | Medium | Low
101 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM17 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Fund Transfer page 4. Enter required fields 5. Press "Submit" button 6. Refresh page 7. Page should redirect to Fund Transfer page | Not redirecting to fund transfer page on clicking refresh button on checking ministatement it is observed that transfer is done twice | High | Medium
102 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM19 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Fund Transfer page 4. Enter wrong Account Number 5. Press "Submit" button 6. System pop-up message "Account doesn't exist" should be shown | A pop up "No details found for this account!!" is shown | Low | Low
103 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM20 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Fund Transfer page 4. Enter Account Number not associated with him 5. Press "Submit" button 6. System pop-up message "You are not authorized to do this" should be shown | Fund Transfer Details are shown | High | Low
104 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM21 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Fund Transfer page 4. Enter same Source and Destination Account Numbers 5. Press "Submit" button 6. System pop-up message "Payers account No and Payees account No Must Not be Same!!!" should be shown | No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown | Medium | Low
105 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM25 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Deposit page 4. Enter required fields 5. Press "Submit" button 6. Refresh page 7. Page should redirect to Deposit Page | 1) "Not redirecting to deposite page on clicking refresh button" 2) Deposit details are updated to the sum entered | High | Medium
106 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM28 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager 3. Navigate to Withdrawal page 4. Enter Account number that has balance lower than withdrawal sum 5. Press "Submit" button 6. An Error message "Transaction failed account balance is low !!" should be shown | Withdrawal details are shown with minus value of balance | High | Medium
107 | Open | Shreyas Bhagat | v3 | 2024-08-02 | SM32 | 1. Open http://demo.guru99.com/V3/index.php 2. Login as a manager/customer 3. Navigate to Customized Statement page 4. Enter Account number 5. Enter From date greater than To Date 6. Press "Submit" button 7. An pop - up "From date field should be lower than to date field" should be shown | Pop-up message "No transaction details found!!!" is shown | Low | Low
(v4)
108 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | CusSta-4-37 | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Amount Lower Limit field blank 5. Press Tab to move to the next field 6. System error: "Amount Lower Limit must not be blank" must be shown | No system error message is shown | Medium | Medium
109 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | CusSta-4-40 | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Leave Number of Transaction field blank 5. Press Tab to move to the next field 6. System error: "Number of transaction must not be blank" must be shown | No system error message is shown | Medium | Medium
110 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | ChaPas-14-103 | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager/customer 3. Navigate to "Change Password" page 4. Enter same passwords to Old Password and New Password fields 5. Confirm New Password and Submit 6. System error: "New Password should not match Old Password" must be shown | No system error message is shown | Medium | Medium
111 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | BalUI_B | 1. Open http://demo.guru99.com/V4/ 2. Login as a manager/customer 3. Navigate to "Balance Enquiry" page 4. Verify that all required fields are marked as "*mandatory fields" | "Account No" field is not marked as mandatory | Low | Low
112 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | FunUI | 1. Open http://demo.guru99.com/V4/ 2. Login as a manager/customer 3. Navigate to "Fund Transfer" page 4. Verify that fields' labels are as required | Description field is present though not mentioned on STR document | Low | Low
113 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | MinUI_B | 1. Open http://demo.guru99.com/V4/ 2. Login as a manager/customer 3. Navigate to "Mini Statement" page 4. Verify that Account No field is marked as "*mandatory fields" | Account No is not marked as mandatory | Low | Low
114 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | CusUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager/customer 3. Navigate to "Customized Statement" page 4. Verify that Account No, Minimum Transaction Value, Number Of Transaction fields are marked as "* mandatory field" | Account Number, Minimum Transaction Value and Number Of Transaction fields are not marked as mandatory | Low | Low
115 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | NewCusUI_A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "New Customer" page 4. Verify that fields' labels are as required | "E-mail" label instead of "Email Id" and Password field is present though not described in STR document | Low | Low
116 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | NewCusUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
117 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | NewAccUI_A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that fields' labels are as required | "Customer id" instead of "Customer Id", "Account type" instead of "Account Type", "submit" instead of "Submit" and "reset" instead of "Reset" labels | Low | Low
118 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | NewAccUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "New Account" page 4. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
119 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | DepUI-A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Deposit" page 4. Verify that fields' labels are as required | "Amount" instead of "Amount Deposut" field | Low | Low
120 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | DepUI-B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Deposit" page 4. Verify that all fields are marked as "* mandatory field" | Account Number, Amount and Description fields are not marked as mandatory | Low | Low
121 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | WitUI-B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Withdrawal" page 4. Verify that all fields are marked as "* mandatory field" | Account Number, Amount and Description fields are not marked as mandatory | Low | Low
122 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | DelCusUI_A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
123 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | DelCusUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Delete Customer" page 4. Verify that all fields are marked as "* mandatory field" | Customer ID is not marked as mandatory field | Low | Low
124 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | EdiAccUI_A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Edit Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
125 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | EdiAccUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Edit Account" page 4. Verify that all fields are marked as "* mandatory field" | Account No field is not marked as mandatory | Low | Low
126 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | EdiAccForUI | 1. Open http://demo.guru99.com/V4/ 2. Login as a manager/customer 3. Navigate to "Edit Account form" page 4. Verify that fields' labels are as required | "Type of Account" instead of "Account Type" and "Savings" instead of "Saving" in dropdown list | Low | Low
127 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | DelAccUI_A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager= 3. Navigate to "Delete Account" page 4. Verify that fields' labels are as required | "Account No" instead of "Account Number" | Low | Low
128 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | DelAccUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager= 3. Navigate to "Delete Account" page 4. Verify that all fields are marked as "* mandatory field" | Account No field is not marked as mandatory | Low | Low
129 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | EdiCusUI_A | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Verify that fields' labels are as required | "Customer ID" instead of "Customer Id" label | Low | Low
130 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | EdiCusUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a manager 3. Navigate to "Edit Customer" page 4. Verify that all fields are marked as "* mandatory field" | Customer ID is not marked as mandatory field | Low | Low
131 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | LogUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Verify that all fields are marked as "* mandatory field" | No fields marked as mandatory | Low | Low
132 | Deferred | Shreyas Bhagat | v3 | 2024-08-02 | HomeUI_B | 1. Open http://demo.guru99.com/V4/index.php 2. Login as a customer 3. Navigate to Home page 4. Verify that fields' labels are as required | "Changepassword" section is mistyped | Low | Low